# Transition standard TS 04

FICTIONAL COMPANY DATA. Version 4, 15 September 2026. Approved by Operations Director for proposal use. Owner: Transition Director. Entity: Alder Services Hong Kong. Scope: Hong Kong managed workplace services.

The approved standard is 20 working days from receipt of an agreed asset register and client access permissions. Days 1-5 validate assets and risks; days 6-15 transfer work orders and train staff; days 16-20 test readiness and agree handover.

The Transition Director is accountable. For issue management, escalation and handover controls, follow the controlled Annex A in annex-a-controls.pdf in this company folder. Those arrangements are not restated here.

This is an approved standard approach, not a tender-specific staffing allocation, unconditional start date or guarantee of uninterrupted service.